Curriculum in Toxicology, UNC-Chapel Hill

2008 Program Review by the Office of the Provost and the Graduate School

- Timeline: Site Visit by Review Team Scheduled for 5-7 November 2008

January - March 2008:
√ Prepared and forwarded to Graduate School by February 15 a ranked list
	  of potential external and internal reviewers (with contact information)
√ The Graduate School selected the following reviewers:

Professor Robert Roth, Michigan State University (Chair)

Professor Cheryl Walker, University of Texas MD Anderson Cancer Center

Professor Rudy Juliano, UNC-CH/Pharmacology (Internal Reviewer)
√ Developed evaluation questionnaire (electronic survey)

April 2008:
√ Posted questionnaire on SurveyMonkey.com (http://www.surveymonkey.com/)

√ Sent survey to current students (4/8/08), Ph.D. graduates (4/11, 14, 19, 29/08), 
    and past postdoctoral trainees (4/29/08)

√ Prepared outline of report before trainees’ meeting

√ Meeting of current graduate students to discuss the status of the Ph.D. program,
    review its strengths and weaknesses from their perspective, and offer their 
    concerns and suggestions for the future
    Scheduled date: Monday, April 21st, at the LCCC Pagano conference room (plaza 
    level) starting immediately after the TOXC722 weekly seminar (pizza, soft drinks 
    and cookies provided)

May and June 2008:
√ Current students prepared their written report before faculty retreat (no faculty
    involvement)
√ Oral summary of report to TOXC Executive Committee by students’
    representatives (5/15/08)
√ Tabulation of electronic survey responses

√ Preliminary report of electronic survey discussed at the TOXC Executive
    Committee (5/15/08)
√ Students delivered final report to faculty leadership
√ Retreat of Curriculum faculty to discuss draft report and review
    trainees’ comments (presented by students’ leaders)

Date: Thursday, June 12, 1-5:50 pm, Kenan Center

Summer 2008:
√ Preparation of tables, figures, and appendix materials to be included in self-study
    report 
√ Faculty leadership worked on different sections of self-study report 
√ Graduate Education Committee reviewed and approved section B (Curriculum)

September 2008:
√ Faculty leadership completed the first draft of self-study report
√ Faculty representatives invited to review, help edit and complete
    the final copy of self-study report

October 2008:
√ Self-study report approved by the Executive Committee
√ Copies of the self-study report submitted to the Graduate School (10/3/08)
√ Final copy of the self-study report made available to faculty and students
√ Agenda for the site visit prepared and submitted to Graduate School for review